## Sheet1
Task Name | Duration | Contributor | Role | Start | End
Project Management:
Work flow of app |  | Danial Agha | Project Manager
Business Analyst: | 2 Days
Requirements Gathering |  | Talha Ahmed | Business Analyst | 30/12/23 | 2024-04-01
App Analysis |  | Talha Ahmed | Business Analyst
UI/UX Design:
Create UI design on illustrator | 1 week | Muhammad Muzammil | UI Designer | 2024-03-01 | 7/1/24 , 14/1/24
App Frontend : | 4 Days/person
Start Screen |  | Khalid Ghulam | App Frontend | 2024-11-01 | 17/1/24
Login and Registration Screen |  | Khalid Ghulam | App Frontend | 2024-11-01 | 17/1/24
Passenger home screen |  | Ebad Ur Renhman | App Frontend | 2024-11-01 | 17/1/24
Toggle |  | Ebad Ur Renhman | App Frontend | 2024-11-01 | 17/1/24
Profile Screen |  | Ebad Ur Renhman | App Frontend | 2024-11-01 | 17/1/24
Driver Home screen |  | Khalid Ghulam | App Frontend | 2024-11-01 | 17/1/24
Add Ride Screen |  | Ebad Ur Renhman | App Frontend | 2024-11-01 | 17/1/24
Add Vehicle Details Screen |  | Ebad Ur Renhman | App Frontend | 2024-11-01 | 17/1/24
Splash Screen |  | Ebad Ur Renhman | App Frontend | 2024-11-01 | 17/1/24
App Backend: | 9 Days
Login and Registeration Authentication |  | Aajiz Ali | App Backend | 2024-01-18 | 2024-01-22
Saving ride info. of driver In database |  | Aajiz Ali | App Backend | 2024-01-18 | 2024-01-22
Showing ride info. To the passenger |  | Zubair Ali | App Backend | 2024-01-23 | 2024-01-27
Saving vehicle details in the database |  | Zubair Ali | App Backend | 2024-01-23 | 2024-01-27
Showing user name on the home screen |  | Kamran | App Backend | 2024-01-23 | 2024-01-27
Keep the user logged-in when app is closed |  | Kamran | App Backend | 2024-01-23 | 2024-01-27
Tester: | 1 Day
Test Cases |  | Asad Irshad | App Tester | 27/1/24 | 27/1/24